## Slide 1
Houston 2006
1:00 PM: 180 flight hours requested
6 weeks in the field requested
August 1 to September 15
1:01 PM: overview from Fred
draft science plan available:
effteepee.al.noaa.gov/fred/2006texaqs(v5).doc
userid: aeronomy
pword: (please ask)
1:11 PM: P-3 instrument layout and planning
Newly minted documents for investigators
Installation, shipping, deadlines(!), etc.
2:00 PM: Questions and answers …
<3:00 PM: adjourn

## Slide 2
Houston 2006
2004: The aircraft was loaded to capacity, and very hot
2006: We’re adding several new instruments …
particulate phase
extinction (CRDS) Sta. 2 Tahlee AL
absorption (PSAP) Sta. 2 Tahlee AL
particle size (UHSAS) Sta. 2 Chuck AL
CCN (CCN) Sta. 2 floor Jeessy GIT
soot fraction (SP2) AMPS pod Shuka AL
AMS (TOF-MS) Sta. 3 Ann/Jose AL/CU
gas phase
ethylene (photoacoustics) Sta. 6 or 8 Joost/Carsten AL
… by losing PALMS, MIDAS, and SSFR, and
shuffling around most of the rest.
Temperature, weight, and footprint are critical issues for 2006.

## Slide 3
Houston 2006
Minimizing anticipated temperature problems:
On the ground:
• AL/AOC will be leasing two large, industrial-size air
conditioning units to chill the cabin in preflight/postflight
• LIPF (“pump bay”) to be directly cooled by a third AC unit
• Minimum # of personnel permitted aboard in pre/postflight
In flight:
• Discussing options with AOC for improved in-flight cooling,
and improved air circulation throughout cabin
• Working on improved under-floor air circulation for LIPF
It is likely the cabin will still be quite warm during flight.
Please consider active ventilation of your instrumentation.

## Slide 4
Houston 2006
Minimizing anticipated installation problems:
(instrument weight, footprint, integration, and acceptance)
• New 2-bay electronics racks planned (Sta. 3, C3X, 5, 7; Sta. 4 too?)
Dubé design should save ~50%, or over 300 lbs. overall
pending acceptance by AOC engineering staff
estimated available by August/September
• New custom racks planned (SO2, CIMS chambers, PTRMS/ethene, TOF-AMS)
Simons and Dubé designs should make installation possible
estimated availability on October 1
• much more information and analysis will be required of everyone,
much earlier in the integration process
• surprises will be very difficult, or impossible, to accommodate
• PLEASE ASK FIRST before assuming something small won’t be a problem.

## Slide 5
CO
NO, NO2, NOy, O3; CO2
H2O TDL
Low turbulence
aerosol inlet
White-light optical
particle counter
CCN
Sub-micron aerosol
extinction as f(RH),
total dry extinction;
absorption; size
distributions
PILS; AMS
H2SO4, OH,
(HO2+RO2)
Operators - seats:
NOy/O3/CO2: C3X
CRDS: Sta. 2
PILS/AMS: Sta. 3
CIMS: Sta. 5
CH2O: Sta. 7
NO3, N2O5
ethylene; SO2
actinic fluxes
CH2O; PANs
PTRMS
HNO3, NH3
WAS; NMASS;
soot fraction
Proposed N42 layout - Houston 2006
NOAA-AL 2-26-2005
Red: not yet approved
Blue: approved by CCT

## Slide 6
Houston 2006
• Some window plates will be shared between instruments:
Sta. 5: HNO3, NH3, and (PTRMS or SO2)
Sta. 6: PANs and HCHO
New window plates requested from AOC - will design to spec.
• Ground lines, vacuum, exhaust tubing to be replaced -
Best combination of low cost, light weight, chemical
inertness, non-flammability, ease of installation:
Teflon - costs ca. $6k, saves up to 100 lbs.
Est. 3 people for 1 week in Tampa, mid-April 2005
Any volunteers (besides Chuck, Andy, and Fred?)

## Slide 7
Houston 2006
Newly minted documents, to ease integration woes:
1. PI installation guide (info for you)
2. PI instrument worksheet (info from you)
3. MacDill clearance form
4. Ellington clearance form
“We’re from the government; we’re here to help”

## Slide 8
Houston 2006
1. Information provided in the PI installation guide
(now 12 pages)
Installation considerations
  approved hardware, wiring, mounting, etc.
  available power (total, at each station, and by bus)
Hazardous materials usage
Inlet recommendations
Pump and exhaust considerations
Miscellaneous
  Operational procedures (preflight & postflight, non-flight days)
  Flight tests
Equipment inspection and acceptance by AOC
Please read thoroughly, ask questions, and make comments;
this is an evolving document, as are the AOC regs…

## Slide 9
Houston 2006
2. Information requested in the PI installation worksheet
(now 8 pages)
General info
Accurate total instrument weight, footprint, and power used
Data and plumbing drops requested
Routine aircraft access and support requested (pre-, post-, and non-flight days)
Hazmat used
  Installed in the aircraft (lasers, RF emitters, compressed/toxic/flammable
  gases, radioactive sources, cryogens, UPS/batteries, motors, heaters)
  Used in preflight/postflight/on ground
AOC sheet metal support requests
Requested ferry flight/check flight procedures
Requested laboratory space and facilities at Ellington
Deadline for this information: this calendar year
(sooner, if taking part in test flights)

## Slide 10
Houston 2006
3. Information requested in the MacDill clearance form
(now 1 page)
SSN, DOB, Work info, driver’s license number, citizenship, the usual stuff
Foreign nationals will also need to provide visa information etc.
• Due at least a month before you intend to visit MacDill
• Plan on carrying the original AOC permission letter
with you when checking into the Visitor’s Center
• The badges should be good for the entire mission duration

## Slide 11
Houston 2006
4. Information requested in the Ellington clearance form
(now 0 pages)

## Slide 12
Houston 2006
• Test flights - two possible times
November-early December 2005
January-February 2006
Highly recommended for new instruments/installations
Moves the deadlines for instrument info up substantially
• Please communicate your decision, yea or nea, to
me by May 1st, 2005 (within 6 weeks)

## Slide 13
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 14
May
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 15
June
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 16
July
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 17
August
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 18
September
Houston 2006
Tentative schedule:
May 15: P-3 available(?)
May 19: shipments begin
May 22: integration begins
(9 weeks, sequence TBD)
July 24: AOC weight/balance
July 27-31: 2-3 check flights(?)
Aug. 1: transit to Houston
(6 weeks, should be fun)
Sept. 15: transit to Tampa
Sept. 21: relax

## Slide 19
Houston 2006
We’re working on a Houston 2006 Aeronomy Lab P-3 web site
for up-to-date documents, schedules, and this presentation:
P3 installation guide.doc
P3 installation worksheet.doc
MacDill clearance form.doc
Texas 2006 schedule.pdf
March 16 2005 TR.ppt

## Slide 20
Houston 2006
• Likely at Ellington again, on Hangar 990 ramp
hope to secure lab space in zero-G lab
• Office space TBD
• No provisions yet for travel and lodging arrangements
If you find a good place to stay, please let us know…
• Questions? Comments? Concerns?